## 5Y Renewal
2025-07-17
EMA/461220/2015 Rev.4
Human Medicines Division | The timetables in this document may be subject to revision
Marketing authorisation renewal application
Assessment of initial submission (90-day timetable)
Assessment of responses to Request for Supplementary Information (30-day timetable after clock-stop for responses)
Assessment of responses to Request for Supplementary Information (30-day timetable after immediate responses)
Official address Domenico Scarlattilaan 6 ● 1083 HS Amsterdam ● The Netherlands
Address for visits and deliveries Refer to www.ema.europa.eu/how-to-find-us
Send us a question Go to www.ema.europa.eu/contact
Telephone +31 (0)88 781 6000
An agency of the European Union

## 90D initial phase
Assessment of initial submission
90-day timetable
| Deadline for Submission (*) | Start date (^) | CHMP and PRAC Rapporteur Joint AR | Comments from PRAC and CHMP (**) | Updated CHMP and PRAC Rapporteur Joint AR (***) | PRAC outcome | Request for Supplementary Information (RSI) or Opinion
A1 | 2024-10-16 | 2024-11-02 | 2025-01-02 | 2025-01-06 | 2025-01-09 | 2025-01-16 | 2025-01-30
A2 | 2024-11-13 | 2024-11-30 | 2025-01-28 | 2025-02-03 | 2025-02-06 | 2025-02-13 | 2025-02-27
A3 | 2024-12-02 | 2024-12-28 | 2025-02-25 | 2025-03-03 | 2025-03-06 | 2025-03-13 | 2025-03-27
A4 | 2025-01-09 | 2025-01-26 | 2025-03-25 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-25
A5 | 2025-02-05 | 2025-02-22 | 2025-04-22 | 2025-04-28 | 2025-05-02 | 2025-05-08 | 2025-05-22
A6 | 2025-03-05 | 2025-03-22 | 2025-05-20 | 2025-05-26 | 2025-05-28 | 2025-06-05 | 2025-06-19
A7 | 2025-04-08 | 2025-04-26 | 2025-06-24 | 2025-06-30 | 2025-07-03 | 2025-07-10 | 2025-07-24
A8
A9 | 2025-06-04 | 2025-06-21 | 2025-08-19 | 2025-08-25 | 2025-08-28 | 2025-09-04 | 2025-09-18
A10 | 2025-07-02 | 2025-07-19 | 2025-09-16 | 2025-09-22 | 2025-09-25 | 2025-10-02 | 2025-10-16
A11 | 2025-07-30 | 2025-08-16 | 2025-10-14 | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-13
A12 | 2025-08-27 | 2025-09-13 | 2025-11-11 | 2025-11-17 | 2025-11-20 | 2025-11-27 | 2025-12-11
A13 | 2025-10-15 | 2025-11-01 | 2025-12-22 | 2026-01-05 | 2026-01-08 | 2026-01-15 | 2026-01-29
A14 | 2025-11-12 | 2025-11-29 | 2026-01-27 | 2026-02-02 | 2026-02-05 | 2026-02-12 | 2026-02-26
A15 | 2025-12-02 | 2025-12-27 | 2026-02-24 | 2026-03-02 | 2026-03-05 | 2026-03-12 | 2026-03-26
A16 | 2026-01-07 | 2026-01-24 | 2026-03-24 | 2026-03-30 | 2026-04-01 | 2026-04-10 | 2026-04-23
A17 | 2026-02-04 | 2026-02-21 | 2026-04-21 | 2026-04-28 | 2026-04-30 | 2026-05-07 | 2026-05-21
A18 | 2026-03-11 | 2026-03-28 | 2026-05-26 | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-25
A19 | 2026-04-08 | 2026-04-25 | 2026-06-23 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 2026-07-23
A20
A21 | 2026-06-03 | 2026-06-20 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-09-03 | 2026-09-17
A22 | 2026-07-01 | 2026-07-18 | 2026-09-15 | 2026-09-21 | 2026-09-24 | 2026-10-01 | 2026-10-15
A23 | 2026-07-29 | 2026-08-15 | 2026-10-13 | 2026-10-19 | 2026-10-22 | 2026-10-29 | 2026-11-12
A24 | 2026-08-26 | 2026-09-12 | 2026-11-10 | 2026-11-16 | 2026-11-19 | 2026-11-26 | 2026-12-10
A25 | 2026-10-14 | 2026-10-31 | 2026-12-22 | 2027-01-04 | 2027-01-08 | 2027-01-14 | 2027-01-28
A26 | 2026-11-11 | 2026-11-28 | 2027-01-26 | 2027-02-01 | 2027-02-04 | 2027-02-11 | 2027-02-25
A27 | 2026-12-02 | 2027-01-03 | 2027-03-02 | 2027-03-08 | 2027-03-11 | 2027-03-18 | 2027-04-02
A28 | 2027-01-14 | 2027-01-31 | 2027-03-30 | 2027-04-05 | 2027-04-08 | 2027-04-15 | 2027-04-30
A29 | 2027-02-10 | 2027-02-27 | 2027-04-28 | 2027-05-03 | 2027-05-05 | 2027-05-13 | 2027-05-27
A30 | 2027-03-08 | 2027-03-27 | 2027-05-25 | 2027-05-31 | 2027-06-03 | 2027-06-10 | 2027-06-24
A31 | 2027-04-07 | 2027-04-24 | 2027-06-22 | 2027-06-28 | 2027-07-01 | 2027-07-08 | 2027-07-22
A32
A33 | 2027-06-02 | 2027-06-19 | 2027-08-17 | 2027-08-23 | 2027-08-26 | 2027-09-02 | 2027-09-16
A34 | 2027-06-30 | 2027-07-17 | 2027-09-14 | 2027-09-20 | 2027-09-23 | 2027-09-30 | 2027-10-14
A35 | 2027-07-28 | 2027-08-14 | 2027-10-12 | 2027-10-18 | 2027-10-21 | 2027-10-28 | 2027-11-11
A36 | 2027-09-01 | 2027-09-18 | 2027-11-16 | 2027-11-22 | 2027-11-25 | 2027-12-02 | 2027-12-16
(*) Renewal applications must be submitted at least nine months before the actual expiry date of the marketing
authorisation, i.e. the 5-year anniversary of the Commission Decision granting or renewing the marketing
authorisation and irrespective of whether the marketing authorisation may be suspended. The start of the
evaluation process will be the next possible date in the table after submission and validation of the dossier.
The MAHs should agree in advance the submission date of the renewal application with the Agency.
The Agency strongly recommends submitting the application before the published submission deadline. This is to
avoid missing the target start date as a result of a technically invalid eCTD submission, in which case the
submission is considered void and it needs to be re-despatched.
(^) The validation period between submission date and start date is usually sixteen calendar days.
(**) Comments from PRAC and CHMP members are not made available to Marketing Authorisation Holders.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CHMP)
members which create the need for the update.

## 30D Resp phase after clockstop
Assessment of responses to Request for Supplementary Information
30-day timetable after clock-stop for responses
| Deadline for Submission (*) | Re-start date | CHMP and PRAC Rapporteur Joint AR | Comments from PRAC and CHMP (**) | Updated CHMP and PRAC Rapporteur Joint AR (***) | PRAC outcome | Opinion
B1 | 2024-12-20 | 2025-01-01 | 2025-01-06 | 2025-01-08 | 2025-01-09 | 2025-01-16 | 2025-01-30
B2 | 2025-01-28 | 2025-01-29 | 2025-02-03 | 2025-02-05 | 2025-02-06 | 2025-02-13 | 2025-02-27
B3 | 2025-02-25 | 2025-02-26 | 2025-03-03 | 2025-03-05 | 2025-03-06 | 2025-03-13 | 2025-03-27
B4 | 2025-03-26 | 2025-03-27 | 2025-03-31 | 2025-04-02 | 2025-04-03 | 2025-04-10 | 2025-04-25
B5 | 2025-04-22 | 2025-04-23 | 2025-04-28 | 2025-04-30 | 2025-05-02 | 2025-05-08 | 2025-05-22
B6 | 2025-05-20 | 2025-05-21 | 2025-05-26 | 2025-05-28 | 2025-05-28 | 2025-06-05 | 2025-06-19
B7 | 2025-06-24 | 2025-06-25 | 2025-06-30 | 2025-07-02 | 2025-07-03 | 2025-07-10 | 2025-07-24
B8
B9 | 2025-08-19 | 2025-08-20 | 2025-08-25 | 2025-08-27 | 2025-08-28 | 2025-09-04 | 2025-09-18
B10 | 2025-09-16 | 2025-09-17 | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-10-02 | 2025-10-16
B11 | 2025-10-14 | 2025-10-15 | 2025-10-20 | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-11-13
B12 | 2025-11-11 | 2025-11-12 | 2025-11-17 | 2025-11-19 | 2025-11-20 | 2025-11-27 | 2025-12-11
B13 | 2025-12-23 | 2025-12-31 | 2026-01-05 | 2026-01-07 | 2026-01-08 | 2026-01-15 | 2026-01-29
B14 | 2026-01-27 | 2026-01-28 | 2026-02-02 | 2026-02-04 | 2026-02-05 | 2026-02-12 | 2026-02-26
B15 | 2026-02-24 | 2026-02-25 | 2026-03-02 | 2026-03-04 | 2026-03-05 | 2026-03-12 | 2026-03-26
B16 | 2026-03-24 | 2026-03-25 | 2026-03-30 | 2026-04-01 | 2026-04-01 | 2026-04-10 | 2026-04-23
B17 | 2026-04-21 | 2026-04-22 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-07 | 2026-05-21
B18 | 2026-05-26 | 2026-05-27 | 2026-06-01 | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-25
B19 | 2026-06-23 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 2026-07-02 | 2026-07-09 | 2026-07-23
B20
B21 | 2026-08-18 | 2026-08-19 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-03 | 2026-09-17
B22 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 2026-09-24 | 2026-10-01 | 2026-10-15
B23 | 2026-10-13 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 2026-10-22 | 2026-10-29 | 2026-11-12
B24 | 2026-11-10 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 2026-11-19 | 2026-11-26 | 2026-12-10
B25 | 2026-12-23 | 2026-12-30 | 2027-01-04 | 2027-01-06 | 2027-01-08 | 2027-01-14 | 2027-01-28
B26 | 2027-01-26 | 2027-01-27 | 2027-02-01 | 2027-02-03 | 2027-02-04 | 2027-02-11 | 2027-02-25
B27 | 2027-03-03 | 2027-03-04 | 2027-03-08 | 2027-03-10 | 2027-03-11 | 2027-03-18 | 2027-04-02
B28 | 2027-03-31 | 2027-04-01 | 2027-04-05 | 2027-04-07 | 2027-04-08 | 2027-04-15 | 2027-04-30
B29 | 2027-04-26 | 2027-04-28 | 2027-05-03 | 2027-05-05 | 2027-05-05 | 2027-05-13 | 2027-05-27
B30 | 2027-05-25 | 2027-05-26 | 2027-05-31 | 2027-06-02 | 2027-06-03 | 2027-06-10 | 2027-06-24
B31 | 2027-06-22 | 2027-06-23 | 2027-06-28 | 2027-06-30 | 2027-07-01 | 2027-07-08 | 2027-07-22
B32
B33 | 2027-08-17 | 2027-08-18 | 2027-08-23 | 2027-08-25 | 2027-08-26 | 2027-09-02 | 2027-09-16
B34 | 2027-09-14 | 2027-09-15 | 2027-09-20 | 2027-09-22 | 2027-09-23 | 2027-09-30 | 2027-10-14
B35 | 2027-10-12 | 2027-10-13 | 2027-10-18 | 2027-10-20 | 2027-10-21 | 2027-10-28 | 2027-11-11
B36 | 2027-11-16 | 2027-11-17 | 2027-11-22 | 2027-11-24 | 2027-11-25 | 2027-12-02 | 2027-12-16
(*) The Agency strongly recommends submitting the application before the published submission deadline.
This is to avoid missing the target start date as a result of a technically invalid eCTD submission, in which case
the submission is considered void and it needs to be re-despatched.
(**) Comments from PRAC and CHMP members are not made available to Marketing Authorisation Holders.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CHMP)
members which create the need for the update.

## 30D Resp phase after imm resp
Assessment of responses to Request for Supplementary Information
30-day timetable after immediate responses1
| Deadline for Submission (*) | Re-start date | CHMP and PRAC Rapporteur Joint AR | PRAC outcome | Comments from CHMP (**) | Updated CHMP and PRAC Rapporteur Joint AR (***) | Opinion
C1 | 2024-12-20 | 2025-01-01 | 2025-01-15 | 2025-01-16 | 2025-01-20 | 2025-01-23 | 2025-01-30
C2 | 2025-02-04 | 2025-02-05 | 2025-02-12 | 2025-02-13 | 2025-02-17 | 2025-02-20 | 2025-02-27
C3 | 2025-03-04 | 2025-03-05 | 2025-03-12 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-03-27
C4 | 2025-04-02 | 2025-04-03 | 2025-04-09 | 2025-04-10 | 2025-04-14 | 2025-04-16 | 2025-04-25
C5 | 2025-04-29 | 2025-04-30 | 2025-05-07 | 2025-05-08 | 2025-05-12 | 2025-05-15 | 2025-05-22
C6 | 2025-05-27 | 2025-05-28 | 2025-06-04 | 2025-06-05 | 2025-06-10 | 2025-06-12 | 2025-06-19
C7 | 2025-06-26 | 2025-06-27 | 2025-07-09 | 2025-07-10 | 2025-07-14 | 2025-07-17 | 2025-07-24
C8
C9 | 2025-08-19 | 2025-08-20 | 2025-09-03 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-18
C10 | 2025-09-23 | 2025-09-24 | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-09 | 2025-10-16
C11 | 2025-10-21 | 2025-10-22 | 2025-10-29 | 2025-10-30 | 2025-11-03 | 2025-11-06 | 2025-11-13
C12 | 2025-11-18 | 2025-11-19 | 2025-11-26 | 2025-11-27 | 2025-12-01 | 2025-12-04 | 2025-12-11
C13 | 2025-12-23 | 2025-12-31 | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-22 | 2026-01-29
C14 | 2026-02-03 | 2026-02-04 | 2026-02-11 | 2026-02-12 | 2026-02-16 | 2026-02-19 | 2026-02-26
C15 | 2026-03-03 | 2026-03-04 | 2026-03-11 | 2026-03-12 | 2026-03-16 | 2026-03-19 | 2026-03-26
C16 | 2026-03-31 | 2026-04-01 | 2026-04-08 | 2026-04-10 | 2026-04-13 | 2026-04-16 | 2026-04-23
C17 | 2026-04-28 | 2026-04-29 | 2026-05-06 | 2026-05-07 | 2026-05-11 | 2026-05-13 | 2026-05-21
C18 | 2026-05-28 | 2026-05-29 | 2026-06-10 | 2026-06-11 | 2026-06-15 | 2026-06-18 | 2026-06-25
C19 | 2026-06-30 | 2026-07-01 | 2026-07-08 | 2026-07-09 | 2026-07-13 | 2026-07-16 | 2026-07-23
C20
C21 | 2026-08-18 | 2026-08-19 | 2026-09-02 | 2026-09-03 | 2026-09-07 | 2026-09-10 | 2026-09-17
C22 | 2026-09-22 | 2026-09-23 | 2026-09-30 | 2026-10-01 | 2026-10-05 | 2026-10-08 | 2026-10-15
C23 | 2026-10-20 | 2026-10-21 | 2026-10-28 | 2026-10-29 | 2026-11-03 | 2026-11-05 | 2026-11-12
C24 | 2026-11-17 | 2026-11-18 | 2026-11-25 | 2026-11-26 | 2026-11-30 | 2026-12-03 | 2026-12-10
C25 | 2027-01-05 | 2027-01-06 | 2027-01-13 | 2027-01-14 | 2027-01-18 | 2027-01-21 | 2027-01-28
C26 | 2027-02-02 | 2027-02-03 | 2027-02-10 | 2027-02-11 | 2027-02-15 | 2027-02-18 | 2027-02-25
C27 | 2027-03-05 | 2027-03-06 | 2027-03-17 | 2027-03-18 | 2027-03-22 | 2027-03-24 | 2027-04-02
C28 | 2027-04-07 | 2027-04-08 | 2027-04-14 | 2027-04-15 | 2027-04-19 | 2027-04-22 | 2027-04-30
C29 | 2027-05-04 | 2027-05-05 | 2027-05-12 | 2027-05-13 | 2027-05-18 | 2027-05-20 | 2027-05-27
C30 | 2027-06-01 | 2027-06-02 | 2027-06-09 | 2027-06-10 | 2027-06-14 | 2027-06-17 | 2027-06-24
C31 | 2027-06-29 | 2027-06-30 | 2027-07-07 | 2027-07-08 | 2027-07-12 | 2027-07-15 | 2027-07-22
C32
C33 | 2027-08-24 | 2027-08-25 | 2027-09-01 | 2027-09-02 | 2027-09-06 | 2027-09-09 | 2027-09-16
C34 | 2027-09-21 | 2027-09-22 | 2027-09-29 | 2027-09-30 | 2027-10-04 | 2027-10-07 | 2027-10-14
C35 | 2027-10-19 | 2027-10-20 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-11-04 | 2027-11-11
C36 | 2027-11-18 | 2027-11-19 | 2027-12-01 | 2027-12-02 | 2027-12-06 | 2027-12-09 | 2027-12-16
(¹) This timetable is only applicable when minor issues remain.
(*) The Agency strongly recommends submitting the application before the published submission deadline.
This is to avoid missing the target start date as a result of a technically invalid eCTD submission, in which case
the submission is considered void and it needs to be re-despatched.
(**) Comments from CHMP members are not made available to Marketing Authorisation Holders.
(***) An updated AR is optional and dependent on the comments received from CHMP members which create
the need for the update.

## Version tracking
Version 4
Dates for 2027 added in all tabs