## TII
2026-06-16
EMA/727192/2017 Rev.5
Human Medicines Division | The timetables in this document may be subject to revision
Type II variation and worksharing application assessment timetables - ATMP
Initial submission assessment timetable
90-day
60-day
30-day
Responses to Request for Supplementary Information (RSI) assessment timetable
60-day after clockstop
30-day after clockstop
30-day after immediate responses
Official address Domenico Scarlattilaan 6 ● 1083 HS Amsterdam ● The Netherlands
Address for visits and deliveries Refer to www.ema.europa.eu/how-to-find-us
Send us a question Go to www.ema.europa.eu/contact
Telephone +31 (0)88 781 6000
An agency of the European Union

## 90D Initial phase
90-day initial submission assessment timetable¬
| Deadline for Submission (*) | Start date (^) | CAT (Co-) Rapporteur AR | PRAC Rapporteur AR (~) | Comments from PRAC (**) (~) | Updated PRAC Rapporteur AR (***) (~) | Comments from CAT and CHMP (**) | PRAC outcome (~) | Updated CAT Rapporteur(s Joint) AR (***) | CAT Request for Supplementary Information (RSI) or Opinion | CHMP Opinion (#)
A1 | 2025-10-15 | 2025-11-01 | 2025-12-23 | 2026-01-02 | 2026-01-07 | 2026-01-08 | 2026-01-13 | 2026-01-15 | 2026-01-19 | 2026-01-23 | 2026-01-29
A2 | 2025-11-12 | 2025-11-29 | 2026-01-23 | 2026-01-30 | 2026-02-04 | 2026-02-05 | 2026-02-10 | 2026-02-12 | 2026-02-16 | 2026-02-20 | 2026-02-26
A3 | 2025-12-02 | 2025-12-27 | 2026-02-20 | 2026-02-27 | 2026-03-04 | 2026-03-05 | 2026-03-10 | 2026-03-12 | 2026-03-16 | 2026-03-20 | 2026-03-26
A4 | 2026-01-07 | 2026-01-24 | 2026-03-20 | 2026-03-27 | 2026-03-31 | 2026-04-01 | 2026-04-07 | 2026-04-09 | 2026-04-13 | 2026-04-17 | 2026-04-23
A5 | 2026-02-02 | 2026-02-19 | 2026-04-17 | 2026-04-24 | 2026-04-29 | 2026-04-30 | 2026-05-05 | 2026-05-07 | 2026-05-11 | 2026-05-13 | 2026-05-21
A6 | 2026-03-11 | 2026-03-28 | 2026-05-22 | 2026-05-29 | 2026-06-03 | 2026-06-04 | 2026-06-09 | 2026-06-11 | 2026-06-15 | 2026-06-19 | 2026-06-25
A7 | 2026-04-08 | 2026-04-25 | 2026-06-19 | 2026-06-26 | 2026-07-01 | 2026-07-02 | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-17 | 2026-07-23
A8
A9 | 2026-06-03 | 2026-06-20 | 2026-08-14 | 2026-08-21 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-11 | 2026-09-17
A10 | 2026-07-01 | 2026-07-18 | 2026-09-11 | 2026-09-18 | 2026-09-23 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-05 | 2026-10-09 | 2026-10-15
A11 | 2026-07-29 | 2026-08-15 | 2026-10-09 | 2026-10-16 | 2026-10-21 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-03 | 2026-11-06 | 2026-11-12
A12 | 2026-08-26 | 2026-09-12 | 2026-11-06 | 2026-11-13 | 2026-11-18 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-04 | 2026-12-10
A13 | 2026-10-14 | 2026-10-31 | 2026-12-23 | 2027-01-04 | 2027-01-06 | 2027-01-07 | 2027-01-12 | 2027-01-14 | 2027-01-18 | 2027-01-22 | 2027-01-28
A14 | 2026-11-11 | 2026-11-28 | 2027-01-22 | 2027-01-29 | 2027-02-03 | 2027-02-04 | 2027-02-09 | 2027-02-11 | 2027-02-15 | 2027-02-19 | 2027-02-25
A15 | 2026-12-01 | 2026-12-31 | 2027-02-26 | 2027-03-05 | 2027-03-10 | 2027-03-11 | 2027-03-16 | 2027-03-18 | 2027-03-22 | 2027-03-24 | 2027-04-02
A16 | 2027-01-13 | 2027-01-30 | 2027-03-24 | 2027-04-02 | 2027-04-07 | 2027-04-08 | 2027-04-13 | 2027-04-15 | 2027-04-19 | 2027-04-23 | 2027-04-30
A17 | 2027-02-10 | 2027-02-27 | 2027-04-23 | 2027-04-30 | 2027-05-04 | 2027-05-05 | 2027-05-11 | 2027-05-13 | 2027-05-18 | 2027-05-21 | 2027-05-27
A18 | 2027-03-10 | 2027-03-27 | 2027-05-21 | 2027-05-28 | 2027-06-02 | 2027-06-03 | 2027-06-08 | 2027-06-10 | 2027-06-14 | 2027-06-18 | 2027-06-24
A19 | 2027-04-07 | 2027-04-24 | 2027-06-18 | 2027-06-25 | 2027-06-30 | 2027-07-01 | 2027-07-06 | 2027-07-08 | 2027-07-12 | 2027-07-16 | 2027-07-22
A20
A21 | 2027-06-02 | 2027-06-19 | 2027-08-13 | 2027-08-20 | 2027-08-25 | 2027-08-26 | 2027-08-31 | 2027-09-02 | 2027-09-06 | 2027-09-10 | 2027-09-16
A22 | 2027-06-30 | 2027-07-17 | 2027-09-10 | 2027-09-17 | 2027-09-22 | 2027-09-23 | 2027-09-28 | 2027-09-30 | 2027-10-04 | 2027-10-08 | 2027-10-14
A23 | 2027-07-28 | 2027-08-14 | 2027-10-08 | 2027-10-15 | 2027-10-20 | 2027-10-21 | 2027-10-26 | 2027-10-28 | 2027-10-29 | 2027-11-05 | 2027-11-11
A24 | 2027-09-01 | 2027-09-18 | 2027-11-12 | 2027-11-19 | 2027-11-24 | 2027-11-25 | 2027-11-30 | 2027-12-02 | 2027-12-06 | 2027-12-10 | 2027-12-16
A25 | 13/10/2027 | 2027-10-30 | 2027-12-22 | 2028-01-04 | 2028-01-06 | 2028-01-07 | 2028-01-11 | 2028-01-13 | 2028-01-17 | 2028-01-21
A26 | 10/11/2027 | 2027-11-27 | 2028-01-21 | 2028-01-28 | 2028-02-02 | 2028-02-03 | 2028-02-08 | 2028-02-10 | 2028-02-14 | 2028-02-18
A27 | 08/12/2027 | 2027-12-25 | 2028-02-18 | 2028-02-25 | 2028-03-01 | 2028-03-02 | 2028-03-07 | 2028-03-09 | 2028-03-13 | 2028-03-17
A28 | 03/01/2028 | 2028-01-20 | 17/03/2028 | 24/03/2028 | 29/03/2028 | 30/03/2028 | 04/04/2028 | 06/04/2028 | 10/04/2028 | 2028-04-12
A29 | 02/02/2028 | 2028-02-19 | 2028-04-12 | 2028-04-21 | 2028-04-26 | 2028-04-26 | 2028-05-02 | 2028-05-04 | 2028-05-08 | 2028-05-12
A30 | 08/03/2028 | 2028-03-25 | 2028-05-19 | 2028-05-24 | 2028-05-31 | 2028-06-01 | 2028-06-06 | 2028-06-08 | 2028-06-12 | 2028-06-16
A31 | 05/04/2028 | 2028-04-22 | 2028-06-16 | 2028-06-23 | 2028-06-28 | 2028-06-29 | 2028-07-04 | 2028-07-06 | 2028-07-10 | 2028-07-14
A32
A33 | 31/05/2028 | 2028-06-17 | 2028-08-11 | 2028-08-18 | 2028-08-23 | 2028-08-24 | 2028-08-29 | 2028-08-31 | 2028-09-04 | 2028-09-08
A34 | 28/06/2028 | 2028-07-15 | 2028-09-08 | 2028-09-15 | 2028-09-20 | 2028-09-21 | 2028-09-26 | 2028-09-28 | 2028-10-02 | 2028-10-06
A35 | 23/07/2028 | 2028-08-09 | 2028-10-03 | 2028-10-10 | 2028-10-15 | 2028-10-16 | 2028-10-21 | 2028-10-23 | 2028-10-27 | 2028-10-31
A36 | 30/08/2028 | 2028-09-16 | 2028-11-10 | 2028-11-17 | 2028-11-22 | 2028-11-23 | 2028-11-28 | 2028-11-30 | 2028-12-04 | 2028-12-08
(¬) This timetable is only applicable to variations concerning a change to or addition of therapeutic indications and potentially to groupings of variations
(in case of grouped variations, a 90-day assessment timetable should be agreed with the Agency at the time of validation of the application).
(^) The validation period between submission date and start date is usually sixteen calendar days.
(*) The Agency strongly recommends submitting the application before the published submission deadline. This is to avoid missing the target start date as a result
of a technically invalid eCTD submission, in which case the submission is considered void and it needs to be re-despatched.
(~) Step applicable only if the submission falls (at least partially) under the remit of the PRAC (typically, when a RMP is submitted).
(**) Comments from CAT, CHMP and PRAC members are not made available to Applicants.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CAT, CHMP) members which create the need for the update.
(#) Step applicable only in case of CAT Opinion (not applicable in case a Request for Supplementary Information is adopted by the CAT).

## 60D Initial phase
60-day initial submission assessment timetable¬
| Deadline for Submission (*) | Start date (^) | CAT Rapporteur AR (!) | CAT Rapporteur AR (~) | PRAC Rapporteur AR (~) | Comments from PRAC (**) (~) | Updated PRAC Rapporteur AR (***) (~) | Comments from CAT and CHMP (**) | PRAC outcome (~) | Updated CAT Rapporteur AR (***) | CAT Request for Supplementary Information (RSI) or Opinion | CHMP Opinion (#)
B1 | 2025-11-14 | 2025-12-01 | 2026-01-05 | 2026-01-02 | 2026-01-02 | 2026-01-07 | 2026-01-08 | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-23 | 2026-01-29
B2 | 2025-11-28 | 2025-12-29 | 2026-02-02 | 2026-01-27 | 2026-01-30 | 2026-02-04 | 2026-02-05 | 2026-02-11 | 2026-02-12 | 2026-02-16 | 2026-02-20 | 2026-02-26
B3 | 2026-01-09 | 2026-01-26 | 2026-03-02 | 2026-02-24 | 2026-02-27 | 2026-03-04 | 2026-03-05 | 2026-03-11 | 2026-03-12 | 2026-03-16 | 2026-03-20 | 2026-03-26
B4 | 2026-02-06 | 2026-02-23 | 2026-03-30 | 2026-03-24 | 2026-03-27 | 2026-03-31 | 2026-04-01 | 2026-04-08 | 2026-04-09 | 2026-04-13 | 2026-04-17 | 2026-04-23
B5 | 2026-03-04 | 2026-03-21 | 2026-04-28 | 2026-04-21 | 2026-04-24 | 2026-04-29 | 2026-04-30 | 2026-05-06 | 2026-05-07 | 2026-05-11 | 2026-05-13 | 2026-05-21
B6 | 2026-04-10 | 2026-04-27 | 2026-06-01 | 2026-05-26 | 2026-05-29 | 2026-06-03 | 2026-06-04 | 2026-06-10 | 2026-06-11 | 2026-06-15 | 2026-06-19 | 2026-06-25
B7 | 2026-05-08 | 2026-05-25 | 2026-06-29 | 2026-06-23 | 2026-06-26 | 2026-07-01 | 2026-07-02 | 2026-07-08 | 2026-07-09 | 2026-07-13 | 2026-07-17 | 2026-07-23
B8
B9 | 2026-07-03 | 2026-07-20 | 2026-08-24 | 2026-08-18 | 2026-08-21 | 2026-08-26 | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-07 | 2026-09-11 | 2026-09-17
B10 | 2026-07-31 | 2026-08-17 | 2026-09-21 | 2026-09-15 | 2026-09-18 | 2026-09-23 | 2026-09-24 | 2026-09-30 | 2026-10-01 | 2026-10-05 | 2026-10-09 | 2026-10-15
B11 | 2026-08-28 | 2026-09-14 | 2026-10-19 | 2026-10-13 | 2026-10-16 | 2026-10-21 | 2026-10-22 | 2026-10-28 | 2026-10-29 | 2026-11-03 | 2026-11-06 | 2026-11-12
B12 | 2026-09-25 | 2026-10-12 | 2026-11-16 | 2026-11-10 | 2026-11-13 | 2026-11-18 | 2026-11-19 | 2026-11-25 | 2026-11-26 | 2026-11-30 | 2026-12-04 | 2026-12-10
B13 | 2026-11-13 | 2026-11-30 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-06 | 2027-01-07 | 2027-01-13 | 2027-01-14 | 2027-01-18 | 2027-01-22 | 2027-01-28
B14 | 2026-12-02 | 2026-12-28 | 2027-02-01 | 2027-01-26 | 2027-01-29 | 2027-02-03 | 2027-02-04 | 2027-02-10 | 2027-02-11 | 2027-02-15 | 2027-02-19 | 2027-02-25
B15 | 2027-01-13 | 2027-01-30 | 2027-03-08 | 2027-03-03 | 2027-03-05 | 2027-03-10 | 2027-03-11 | 2027-03-17 | 2027-03-18 | 2027-03-22 | 2027-03-24 | 2027-04-02
B16 | 2027-02-12 | 2027-03-01 | 2027-04-05 | 2027-03-30 | 2027-04-02 | 2027-04-07 | 2027-04-08 | 2027-04-14 | 2027-04-15 | 2027-04-19 | 2027-04-23 | 2027-04-30
B17 | 2027-03-12 | 2027-03-29 | 2027-05-03 | 2027-04-28 | 2027-04-30 | 2027-05-04 | 2027-05-05 | 2027-05-12 | 2027-05-13 | 2027-05-18 | 2027-05-21 | 2027-05-27
B18 | 2027-04-09 | 2027-04-26 | 2027-05-31 | 2027-05-25 | 2027-05-28 | 2027-06-02 | 2027-06-03 | 2027-06-09 | 2027-06-10 | 2027-06-14 | 2027-06-18 | 2027-06-24
B19 | 2027-05-05 | 2027-05-24 | 2027-06-28 | 2027-06-22 | 2027-06-25 | 2027-06-30 | 2027-07-01 | 2027-07-07 | 2027-07-08 | 2027-07-12 | 2027-07-16 | 2027-07-22
B20
B21 | 2027-07-02 | 2027-07-19 | 2027-08-23 | 2027-08-17 | 2027-08-20 | 2027-08-25 | 2027-08-26 | 2027-09-01 | 2027-09-02 | 2027-09-06 | 2027-09-10 | 2027-09-16
B22 | 2027-07-30 | 2027-08-16 | 2027-09-20 | 2027-09-14 | 2027-09-17 | 2027-09-22 | 2027-09-23 | 2027-09-29 | 2027-09-30 | 2027-10-04 | 2027-10-08 | 2027-10-14
B23 | 2027-08-27 | 2027-09-13 | 2027-10-18 | 2027-10-12 | 2027-10-15 | 2027-10-20 | 2027-10-21 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-11-05 | 2027-11-11
B24 | 2027-10-01 | 2027-10-18 | 2027-11-22 | 2027-11-16 | 2027-11-19 | 2027-11-24 | 2027-11-25 | 2027-12-01 | 2027-12-02 | 2027-12-06 | 2027-12-10 | 2027-12-16
B25 | 12/11/2027 | 2027-11-29 | 2028-01-04 | 2028-01-04 | 2028-01-06 | 2028-01-07 | 2028-01-10 | 2028-01-12 | 2028-01-13 | 2028-01-17 | 2028-01-21 | 2028-01-27
B26 | 10/12/2027 | 2027-12-27 | 2028-01-31 | 2028-01-25 | 2028-01-28 | 2028-02-02 | 2028-02-03 | 2028-02-09 | 2028-02-10 | 2028-02-14 | 2028-02-18 | 2028-02-24
B27 | 07/01/2028 | 2028-01-24 | 2028-02-28 | 2028-02-22 | 2028-02-25 | 2028-03-01 | 2028-03-02 | 2028-03-08 | 2028-03-09 | 2028-03-13 | 2028-03-17 | 2028-03-23
B28 | 02/02/2028 | 2028-02-19 | 27/03/2028 | 21/03/2028 | 24/03/2028 | 29/03/2028 | 30/03/2028 | 05/04/2028 | 06/04/2028 | 10/04/2028 | 2028-04-12 | 2028-04-21
B29 | 03/03/2028 | 2028-03-20 | 2028-04-24 | 2028-04-18 | 2028-04-21 | 2028-04-26 | 2028-04-28 | 2028-05-03 | 2028-05-04 | 2028-05-08 | 2028-05-12 | 2028-05-18
B30 | 07/04/2028 | 2028-04-24 | 2028-05-29 | 2028-05-23 | 2028-05-29 | 2028-05-31 | 2028-06-01 | 2028-06-07 | 2028-06-08 | 2028-06-12 | 2028-06-16 | 2028-06-22
B31 | 05/05/2028 | 2028-05-22 | 2028-06-26 | 2028-06-20 | 2028-06-23 | 2028-06-28 | 2028-06-29 | 2028-07-05 | 2028-07-06 | 2028-07-10 | 2028-07-14 | 2028-07-20
B32
B33 | 30/06/2028 | 2028-07-17 | 2028-08-21 | 2028-08-14 | 2028-08-18 | 2028-08-23 | 2028-08-24 | 2028-08-30 | 2028-08-31 | 2028-09-04 | 2028-09-08 | 2028-09-14
B34 | 28/07/2028 | 2028-08-14 | 2028-09-18 | 2028-09-12 | 2028-09-15 | 2028-09-20 | 2028-09-21 | 2028-09-27 | 2028-09-28 | 2028-10-02 | 2028-10-06 | 2028-10-12
B35 | 22/08/2028 | 2028-09-08 | 2028-10-13 | 2028-10-10 | 2028-10-13 | 2028-10-18 | 2028-10-19 | 2028-10-22 | 2028-10-23 | 2028-10-27 | 2028-10-31 | 2028-11-09
B36 | 29/09/2028 | 2028-10-16 | 2028-11-20 | 2028-11-14 | 2028-11-17 | 2028-11-22 | 2028-11-23 | 2028-11-29 | 2028-11-30 | 2028-12-04 | 2028-12-08 | 2028-12-14
(¬) This is the default timetable for type II variations, unless there are reasons to extend the assesment time to 90 days or reduce it to 30 days.
(*) The Agency strongly recommends submitting the application before the published submission deadline. This is to avoid missing the target start date as a result
of a technically invalid eCTD submission, in which case the submission is considered void and it needs to be re-despatched.
(^) The validation period between submission date and start date is usually sixteen calendar days.
(!) Step applicable if the PRAC is not involved (i.e. no RMP or or results of non-interventional Post-Authorisation Safety Study (PASS) are submitted).
(~) Step applicable only if the submission falls (at least partially) under the remit of the PRAC (typically, when a RMP is submitted). For PRAC-led variations (including only
an RMP or final results of non-interventional PASS with no consequences to Product Information), only the PRAC Rapporteur produces an AR.
(**) Comments from CAT, CHMP and PRAC members are not made available to Applicants.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CAT, CHMP) members which create the need for the update.
(#) Step applicable only in case of CAT Opinion (not applicable in case a Request for Supplementary Information is adopted by the CAT).

## 60D Resp phase
60-day responses (after clockstop) to RSI assessment timetable¬
| Deadline for Submission (*) | Re-start date | CAT Rapporteur AR (!) | CAT Rapporteur AR (~) | PRAC Rapporteur AR (~) | Comments from PRAC (**) (~) | Updated PRAC Rapporteur AR (***) (~) | Comments from CAT and CHMP (**) | PRAC outcome (~) | Updated CAT Rapporteur AR (***) | CAT Request for Supplementary Information (RSI) or Opinion | CHMP Opinion (#)
D1 | 2025-11-24 | 2025-11-25 | 2026-01-05 | 2025-12-23 | 2026-01-02 | 2026-01-08 | 2026-01-08 | 2026-01-13 | 2026-01-15 | 2026-01-19 | 2026-01-23 | 2026-01-29
D2 | 2025-12-22 | 2025-12-23 | 2026-01-27 | 2026-01-23 | 2026-01-29 | 2026-02-03 | 2026-02-05 | 2026-02-10 | 2026-02-12 | 2026-02-16 | 2026-02-20 | 2026-02-26
D3 | 2026-01-19 | 2026-01-20 | 2026-02-24 | 2026-02-20 | 2026-02-26 | 2026-03-03 | 2026-03-05 | 2026-03-10 | 2026-03-12 | 2026-03-16 | 2026-03-20 | 2026-03-26
D4 | 2026-02-16 | 2026-02-17 | 2026-03-24 | 2026-03-20 | 2026-03-26 | 2026-03-31 | 2026-04-01 | 2026-04-07 | 2026-04-10 | 2026-04-13 | 2026-04-17 | 2026-04-23
D5 | 2026-03-13 | 2026-03-15 | 2026-04-21 | 2026-04-17 | 2026-04-23 | 2026-04-28 | 2026-04-30 | 2026-05-05 | 2026-05-07 | 2026-05-11 | 2026-05-13 | 2026-05-21
D6 | 2026-04-20 | 2026-04-21 | 2026-05-26 | 2026-05-22 | 2026-05-28 | 2026-06-02 | 2026-06-04 | 2026-06-09 | 2026-06-11 | 2026-06-15 | 2026-06-19 | 2026-06-25
D7 | 2026-05-18 | 2026-05-19 | 2026-06-23 | 2026-06-19 | 2026-06-25 | 2026-06-30 | 2026-07-02 | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-17 | 2026-07-23
D8
D9 | 2026-07-13 | 2026-07-14 | 2026-08-18 | 2026-08-14 | 2026-08-20 | 2026-08-25 | 2026-08-27 | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-11 | 2026-09-17
D10 | 2026-08-10 | 2026-08-11 | 2026-09-15 | 2026-09-11 | 2026-09-17 | 2026-09-22 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-05 | 2026-10-09 | 2026-10-15
D11 | 2026-09-07 | 2026-09-08 | 2026-10-13 | 2026-10-09 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-03 | 2026-11-06 | 2026-11-12
D12 | 2026-10-05 | 2026-10-06 | 2026-11-10 | 2026-11-06 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-04 | 2026-12-10
D13 | 2026-11-23 | 2026-11-24 | 2027-01-04 | 2026-12-23 | 2027-01-04 | 2027-01-07 | 2027-01-07 | 2027-01-12 | 2027-01-14 | 2027-01-18 | 2027-01-22 | 2027-01-28
D14 | 2026-12-21 | 2026-12-22 | 2027-01-26 | 2027-01-22 | 2027-01-28 | 2027-02-02 | 2027-02-04 | 2027-02-09 | 2027-02-11 | 2027-02-15 | 2027-02-19 | 2027-02-25
D15 | 2027-01-22 | 2027-01-24 | 2027-03-01 | 2027-02-26 | 2027-03-04 | 2027-03-09 | 2027-03-11 | 2027-03-16 | 2027-03-18 | 2027-03-22 | 2027-03-24 | 2027-04-02
D16 | 2027-02-22 | 2027-02-23 | 2027-03-30 | 2027-03-24 | 2027-04-01 | 2027-04-06 | 2027-04-08 | 2027-04-13 | 2027-04-15 | 2027-04-19 | 2027-04-23 | 2027-04-30
D17 | 2027-03-22 | 2027-03-23 | 2027-04-28 | 2027-04-23 | 2027-04-29 | 2027-05-04 | 2027-05-05 | 2027-05-11 | 2027-05-13 | 2027-05-18 | 2027-05-21 | 2027-05-27
D18 | 2027-04-19 | 2027-04-20 | 2027-05-25 | 2027-05-21 | 2027-05-27 | 2027-06-01 | 2027-06-03 | 2027-06-08 | 2027-06-10 | 2027-06-14 | 2027-06-18 | 2027-06-24
D19 | 2027-05-14 | 2027-05-18 | 2027-06-22 | 2027-06-18 | 2027-06-24 | 2027-06-29 | 2027-07-01 | 2027-07-06 | 2027-07-08 | 2027-07-12 | 2027-07-16 | 2027-07-22
D20
D21 | 2027-07-12 | 2027-07-13 | 2027-08-17 | 2027-08-13 | 2027-08-19 | 2027-08-24 | 2027-08-26 | 2027-08-31 | 2027-09-02 | 2027-09-06 | 2027-09-10 | 2027-09-16
D22 | 2027-08-09 | 2027-08-10 | 2027-09-14 | 2027-09-10 | 2027-09-16 | 2027-09-21 | 2027-09-23 | 2027-09-28 | 2027-09-30 | 2027-10-04 | 2027-10-08 | 2027-10-14
D23 | 2027-09-06 | 2027-09-07 | 2027-10-12 | 2027-10-08 | 2027-10-14 | 2027-10-19 | 2027-10-21 | 2027-10-26 | 2027-10-28 | 2027-10-29 | 2027-11-05 | 2027-11-11
D24 | 2027-10-11 | 2027-10-12 | 2027-11-16 | 2027-11-12 | 2027-11-18 | 2027-11-23 | 2027-11-25 | 2027-11-30 | 2027-12-02 | 2027-12-06 | 2027-12-10 | 2027-12-16
D25 | 12/11/2027 | 2027-11-29 | 2028-01-04 | 2028-01-04 | 2028-01-06 | 2028-01-07 | 2028-01-10 | 2028-01-12 | 2028-01-13 | 2028-01-17 | 2028-01-21 | 2028-01-27
D26 | 10/12/2027 | 2027-12-27 | 2028-01-31 | 2028-01-25 | 2028-01-28 | 2028-02-02 | 2028-02-03 | 2028-02-09 | 2028-02-10 | 2028-02-14 | 2028-02-18 | 2028-02-24
D27 | 07/01/2028 | 2028-01-24 | 2028-02-28 | 2028-02-22 | 2028-02-25 | 2028-03-01 | 2028-03-02 | 2028-03-08 | 2028-03-09 | 2028-03-13 | 2028-03-17 | 2028-03-23
D28 | 02/02/2028 | 2028-02-19 | 27/03/2028 | 21/03/2028 | 24/03/2028 | 29/03/2028 | 30/03/2028 | 05/04/2028 | 06/04/2028 | 10/04/2028 | 2028-04-12 | 2028-04-21
D29 | 03/03/2028 | 2028-03-20 | 2028-04-24 | 2028-04-18 | 2028-04-21 | 2028-04-26 | 2028-04-28 | 2028-05-03 | 2028-05-04 | 2028-05-08 | 2028-05-12 | 2028-05-18
D30 | 07/04/2028 | 2028-04-24 | 2028-05-29 | 2028-05-23 | 2028-05-29 | 2028-05-31 | 2028-06-01 | 2028-06-07 | 2028-06-08 | 2028-06-12 | 2028-06-16 | 2028-06-22
D31 | 05/05/2028 | 2028-05-22 | 2028-06-26 | 2028-06-20 | 2028-06-23 | 2028-06-28 | 2028-06-29 | 2028-07-05 | 2028-07-06 | 2028-07-10 | 2028-07-14 | 2028-07-20
D32
D33 | 30/06/2028 | 2028-07-17 | 2028-08-21 | 2028-08-14 | 2028-08-18 | 2028-08-23 | 2028-08-24 | 2028-08-30 | 2028-08-31 | 2028-09-04 | 2028-09-08 | 2028-09-14
D34 | 28/07/2028 | 2028-08-14 | 2028-09-18 | 2028-09-12 | 2028-09-15 | 2028-09-20 | 2028-09-21 | 2028-09-27 | 2028-09-28 | 2028-10-02 | 2028-10-06 | 2028-10-12
D35 | 22/08/2028 | 2028-09-08 | 2028-10-13 | 2028-10-10 | 2028-10-13 | 2028-10-18 | 2028-10-19 | 2028-10-22 | 2028-10-23 | 2028-10-27 | 2028-10-31 | 2028-11-09
D36 | 29/09/2028 | 2028-10-16 | 2028-11-20 | 2028-11-14 | 2028-11-17 | 2028-11-22 | 2028-11-23 | 2028-11-29 | 2028-11-30 | 2028-12-04 | 2028-12-08 | 2028-12-14
(¬) The timeframe for assessment of responses depends on the complexity and amount of data provided by the Marketing Authorisation Holder.
(*) The Agency strongly recommends submitting the application before the published submission deadline. This is to avoid missing the target start date as a result
of a technically invalid eCTD submission, in which case the submission is considered void and it needs to be re-despatched.
(!) Step applicable if the PRAC is not involved (i.e. no RMP or or results of non-interventional Post-Authorisation Safety Study (PASS) are submitted).
(~) Step applicable only if the submission falls (at least partially) under the remit of the PRAC (typically, when a RMP is submitted). For PRAC-led variations (including only
an RMP or final results of non-interventional PASS with no consequences to Product Information), only the PRAC Rapporteur produces an AR.
(**) Comments from CAT, CHMP and PRAC members are not made available to Applicants.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CAT, CHMP) members which create the need for the update.
(#) Step applicable only in case of CAT Opinion (not applicable in case a Request for Supplementary Information is adopted by the CAT).

## 30D Initial phase
30-day initial submission assessment timetable¬
| Deadline for Submission (*) | Start date (^) | PRAC Rapporteur AR (~) | Comments from PRAC (**) (~) | Updated PRAC Rapporteur AR (***) (~) | CAT Rapporteur AR | PRAC outcome (~) | Comments from CAT and CHMP (**) | Updated CAT Rapporteur AR (***) | CAT Request for Supplementary Information (RSI) or Opinion | CHMP Opinion (#)
C1 | 2025-12-19 | 2025-12-31 | 2026-01-05 | 2026-01-07 | 2026-01-08 | 2026-01-13 | 2026-01-15 | 2026-01-16 | 2026-01-19 | 2026-01-23 | 2026-01-29
C2 | 2026-01-16 | 2026-01-28 | 2026-02-02 | 2026-02-04 | 2026-02-05 | 2026-02-10 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-20 | 2026-02-26
C3 | 2026-02-13 | 2026-02-25 | 2026-03-02 | 2026-03-04 | 2026-03-05 | 2026-03-10 | 2026-03-12 | 2026-03-13 | 2026-03-16 | 2026-03-20 | 2026-03-26
C4 | 2026-03-13 | 2026-03-25 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-07 | 2026-04-09 | 2026-04-10 | 2026-04-13 | 2026-04-17 | 2026-04-23
C5 | 2026-04-08 | 2026-04-20 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-05 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-13 | 2026-05-21
C6 | 2026-05-13 | 2026-05-27 | 2026-06-01 | 2026-06-03 | 2026-06-04 | 2026-06-09 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-19 | 2026-06-25
C7 | 2026-06-12 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 2026-07-02 | 2026-07-07 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-17 | 2026-07-23
C8
C9 | 2026-08-07 | 2026-08-19 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-11 | 2026-09-17
C10 | 2026-09-04 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-09 | 2026-10-15
C11 | 2026-10-02 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-10-30 | 2026-11-03 | 2026-11-06 | 2026-11-12
C12 | 2026-10-30 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-12-04 | 2026-12-10
C13 | 2026-12-18 | 2026-12-30 | 2027-01-04 | 2027-01-06 | 2027-01-07 | 2027-01-12 | 2027-01-14 | 2027-01-15 | 2027-01-18 | 2027-01-22 | 2027-01-28
C14 | 2027-01-15 | 2027-01-27 | 2027-02-01 | 2027-02-03 | 2027-02-04 | 2027-02-09 | 2027-02-11 | 2027-02-12 | 2027-02-15 | 2027-02-19 | 2027-02-25
C15 | 2027-02-17 | 2027-03-01 | 2027-03-08 | 2027-03-10 | 2027-03-11 | 2027-03-16 | 2027-03-18 | 2027-03-19 | 2027-03-22 | 2027-03-24 | 2027-04-02
C16 | 2027-03-19 | 2027-03-31 | 2027-04-05 | 2027-04-07 | 2027-04-08 | 2027-04-13 | 2027-04-15 | 2027-04-16 | 2027-04-19 | 2027-04-23 | 2027-04-30
C17 | 2027-04-16 | 2027-04-28 | 2027-05-03 | 2027-05-04 | 2027-05-05 | 2027-05-11 | 2027-05-13 | 2027-05-14 | 2027-05-18 | 2027-05-21 | 2027-05-27
C18 | 2027-05-14 | 2027-05-26 | 2027-05-31 | 2027-06-02 | 2027-06-03 | 2027-06-08 | 2027-06-10 | 2027-06-11 | 2027-06-14 | 2027-06-18 | 2027-06-24
C19 | 2027-06-11 | 2027-06-23 | 2027-06-28 | 2027-06-30 | 2027-07-01 | 2027-07-06 | 2027-07-08 | 2027-07-09 | 2027-07-12 | 2027-07-16 | 2027-07-22
C20
C21 | 2027-08-06 | 2027-08-18 | 2027-08-23 | 2027-08-25 | 2027-08-26 | 2027-08-31 | 2027-09-02 | 2027-09-03 | 2027-09-06 | 2027-09-10 | 2027-09-16
C22 | 2027-09-03 | 2027-09-15 | 2027-09-20 | 2027-09-22 | 2027-09-23 | 2027-09-28 | 2027-09-30 | 2027-10-01 | 2027-10-04 | 2027-10-08 | 2027-10-14
C23 | 2027-10-01 | 2027-10-13 | 2027-10-18 | 2027-10-20 | 2027-10-21 | 2027-10-26 | 2027-10-28 | 2027-10-29 | 2027-10-29 | 2027-11-05 | 2027-11-11
C24 | 2027-11-05 | 2027-11-17 | 2027-11-22 | 2027-11-24 | 2027-11-25 | 2027-11-30 | 2027-12-02 | 2027-12-03 | 2027-12-06 | 2027-12-10 | 2027-12-16
C25 | 2027-12-17 | 2027-12-29 | 2028-01-03 | 2028-01-05 | 2028-01-06 | 2028-01-11 | 2028-01-13 | 2028-01-14 | 2028-01-17 | 2028-01-21 | 2028-01-27
C26 | 2028-01-14 | 2028-01-26 | 2028-01-31 | 2028-02-02 | 2028-02-03 | 2028-02-08 | 2028-02-10 | 2028-02-11 | 2028-02-14 | 2028-02-18 | 2028-02-24
C27 | 2028-02-11 | 2028-02-23 | 2028-02-28 | 2028-03-01 | 2028-03-02 | 2028-03-07 | 2028-03-09 | 2028-03-10 | 2028-03-13 | 2028-03-17 | 2028-03-23
C28 | 2028-03-08 | 2028-03-20 | 27/03/2028 | 29/03/2028 | 30/03/2028 | 04/04/2028 | 06/04/2028 | 07/04/2028 | 10/04/2028 | 2028-04-12 | 2028-04-21
C29 | 2028-04-07 | 2028-04-19 | 2028-04-24 | 2028-04-26 | 2028-04-28 | 2028-05-02 | 2028-05-04 | 2028-05-05 | 2028-05-08 | 2028-05-12 | 2028-05-18
C30 | 2028-05-12 | 2028-05-24 | 2028-05-29 | 2028-05-31 | 2028-06-01 | 2028-06-06 | 2028-06-08 | 2028-06-09 | 2028-06-12 | 2028-06-16 | 2028-06-22
C31 | 2028-06-09 | 2028-06-21 | 2028-06-26 | 2028-06-28 | 2028-06-29 | 2028-07-04 | 2028-07-06 | 2028-07-07 | 2028-07-10 | 2028-07-14 | 2028-07-20
C32
C33 | 2028-08-04 | 2028-08-16 | 2028-08-21 | 2028-08-23 | 2028-08-24 | 2028-08-29 | 2028-08-31 | 2028-09-01 | 2028-09-04 | 2028-09-08 | 2028-09-14
C34 | 2028-09-01 | 2028-09-13 | 2028-09-18 | 2028-09-20 | 2028-09-21 | 2028-09-26 | 2028-09-28 | 2028-09-29 | 2028-10-02 | 2028-10-06 | 2028-10-12
C35 | 2028-09-26 | 2028-10-08 | 2028-10-13 | 2028-10-15 | 2028-10-16 | 2028-10-21 | 2028-10-23 | 2028-10-24 | 2028-10-27 | 2028-10-31 | 2028-11-09
C36 | 2028-11-03 | 2028-11-15 | 2028-11-20 | 2028-11-22 | 2028-11-23 | 2028-11-28 | 2028-11-30 | 2028-12-01 | 2028-12-04 | 2028-12-08 | 2028-12-14
(¬) This timetable applies to the initial assessment of relatively urgent safety variations agreed upfront to be assessed in a short timeframe.
(^) The validation period between submission date and start date is usually eleven calendar days.
(*) The Agency strongly recommends submitting the application before the published submission deadline. This is to avoid missing the target start date as a result
of a technically invalid eCTD submission, in which case the submission is considered void and it needs to be re-despatched.
(~) Step applicable only in case of PRAC involvement (typically if RMP or results of non-interventional Post-Authorisation Safety Study (PASS) are submitted).
(**) Comments from CHMP and PRAC members are not made available to Applicants.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CHMP) members which create the need for the update.
(#) Step applicable only in case of CAT Opinion (not applicable in case a Request for Supplementary Information is adopted by the CAT).

## 30D Resp phase with clock stop
30-day responses (after clockstop) to RSI assessment timetable¬
| Deadline for Submission (*) | Re-start date | PRAC Rapporteur AR (~) | Comments from PRAC (**) (~) | Updated PRAC Rapporteur AR (***) (~) | CAT Rapporteur AR | Comments from CAT and CHMP (**) | PRAC outcome (~) | Updated CAT Rapporteur AR (***) | CAT Request for Supplementary Information (RSI) or Opinion | CHMP Opinion (#)
E1 | 2025-12-23 | 2025-12-25 | 2026-01-02 | 2026-01-06 | 2026-01-08 | 2026-01-08 | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-23 | 2026-01-29
E2 | 2026-01-21 | 2026-01-22 | 2026-01-29 | 2026-02-03 | 2026-02-05 | 2026-02-05 | 2026-02-11 | 2026-02-12 | 2026-02-16 | 2026-02-20 | 2026-02-26
E3 | 2026-02-18 | 2026-02-19 | 2026-02-26 | 2026-03-03 | 2026-03-05 | 2026-03-05 | 2026-03-11 | 2026-03-12 | 2026-03-16 | 2026-03-20 | 2026-03-26
E4 | 2026-03-18 | 2026-03-19 | 2026-03-26 | 2026-03-30 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-09 | 2026-04-13 | 2026-04-17 | 2026-04-23
E5 | 2026-04-13 | 2026-04-14 | 2026-04-23 | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-05-06 | 2026-05-07 | 2026-05-11 | 2026-05-13 | 2026-05-21
E6 | 2026-05-20 | 2026-05-21 | 2026-05-28 | 2026-06-02 | 2026-06-04 | 2026-06-04 | 2026-06-10 | 2026-06-11 | 2026-06-15 | 2026-06-19 | 2026-06-25
E7 | 2026-06-17 | 2026-06-18 | 2026-06-25 | 2026-06-30 | 2026-07-02 | 2026-07-02 | 2026-07-08 | 2026-07-09 | 2026-07-13 | 2026-07-17 | 2026-07-23
E8
E9 | 2026-08-12 | 2026-08-13 | 2026-08-20 | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-07 | 2026-09-11 | 2026-09-17
E10 | 2026-09-09 | 2026-09-10 | 2026-09-17 | 2026-09-22 | 2026-09-24 | 2026-09-24 | 2026-09-30 | 2026-10-01 | 2026-10-05 | 2026-10-09 | 2026-10-15
E11 | 2026-10-07 | 2026-10-08 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-22 | 2026-10-28 | 2026-10-29 | 2026-11-03 | 2026-11-06 | 2026-11-12
E12 | 2026-11-04 | 2026-11-05 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-11-19 | 2026-11-25 | 2026-11-26 | 2026-11-30 | 2026-12-04 | 2026-12-10
E13 | 2026-12-23 | 2026-12-24 | 2027-01-04 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 2027-01-13 | 2027-01-14 | 2027-01-18 | 2027-01-22 | 2027-01-28
E14 | 2027-01-20 | 2027-01-21 | 2027-01-28 | 2027-02-02 | 2027-02-04 | 2027-02-04 | 2027-02-10 | 2027-02-11 | 2027-02-15 | 2027-02-19 | 2027-02-25
E15 | 2027-02-22 | 2027-02-23 | 2027-03-04 | 2027-03-09 | 2027-03-11 | 2027-03-11 | 2027-03-17 | 2027-03-18 | 2027-03-22 | 2027-03-24 | 2027-04-02
E16 | 2027-03-24 | 2027-03-25 | 2027-04-01 | 2027-04-06 | 2027-04-08 | 2027-04-08 | 2027-04-14 | 2027-04-15 | 2027-04-19 | 2027-04-23 | 2027-04-30
E17 | 2027-04-21 | 2027-04-22 | 2027-04-29 | 2027-05-04 | 2027-05-05 | 2027-05-05 | 2027-05-12 | 2027-05-13 | 2027-05-18 | 2027-05-21 | 2027-05-27
E18 | 2027-05-19 | 2027-05-20 | 2027-05-27 | 2027-06-01 | 2027-06-03 | 2027-06-03 | 2027-06-09 | 2027-06-10 | 2027-06-14 | 2027-06-18 | 2027-06-24
E19 | 2027-06-16 | 2027-06-17 | 2027-06-24 | 2027-06-29 | 2027-07-01 | 2027-07-01 | 2027-07-07 | 2027-07-08 | 2027-07-12 | 2027-07-16 | 2027-07-22
E20
E21 | 2027-08-11 | 2027-08-12 | 2027-08-19 | 2027-08-24 | 2027-08-26 | 2027-08-26 | 2027-09-01 | 2027-09-02 | 2027-09-06 | 2027-09-10 | 2027-09-16
E22 | 2027-09-08 | 2027-09-09 | 2027-09-16 | 2027-09-21 | 2027-09-23 | 2027-09-23 | 2027-09-29 | 2027-09-30 | 2027-10-04 | 2027-10-08 | 2027-10-14
E23 | 2027-10-06 | 2027-10-07 | 2027-10-14 | 2027-10-19 | 2027-10-21 | 2027-10-21 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-11-05 | 2027-11-11
E24 | 2027-11-10 | 2027-11-11 | 2027-11-18 | 2027-11-23 | 2027-11-25 | 2027-11-25 | 2027-12-01 | 2027-12-02 | 2027-12-06 | 2027-12-10 | 2027-12-16
E25 | 2027-12-22 | 2027-12-23 | 2028-01-04 | 2028-01-06 | 2028-01-07 | 2028-01-07 | 2028-01-12 | 2028-01-13 | 2028-01-17 | 2028-01-21 | 2028-01-27
E26 | 2028-01-19 | 2028-01-20 | 2028-01-27 | 2028-02-01 | 2028-02-03 | 2028-02-03 | 2028-02-09 | 2028-02-10 | 2028-02-14 | 2028-02-18 | 2028-02-24
E27 | 2028-02-16 | 2028-02-17 | 2028-02-24 | 2028-02-29 | 2028-03-02 | 2028-03-02 | 2028-03-08 | 2028-03-09 | 2028-03-13 | 2028-03-17 | 2028-03-23
E28 | 2028-03-13 | 2028-03-14 | 23/03/2028 | 28/03/2028 | 30/03/2028 | 30/03/2028 | 05/04/2028 | 06/04/2028 | 10/04/2028 | 2028-04-12 | 2028-04-21
E29 | 2028-04-12 | 2028-04-13 | 2028-04-20 | 2028-04-25 | 2028-04-28 | 2028-04-28 | 2028-05-03 | 2028-05-04 | 2028-05-08 | 2028-05-12 | 2028-05-18
E30 | 2028-05-17 | 2028-05-18 | 2028-05-24 | 2028-05-30 | 2028-06-01 | 2028-06-01 | 2028-06-07 | 2028-06-08 | 2028-06-12 | 2028-06-16 | 2028-06-22
E31 | 2028-06-14 | 2028-06-15 | 2028-06-22 | 2028-06-27 | 2028-06-29 | 2028-06-29 | 2028-07-05 | 2028-07-06 | 2028-07-10 | 2028-07-14 | 2028-07-20
E32
E33 | 2028-08-09 | 2028-08-10 | 2028-08-17 | 2028-08-22 | 2028-08-24 | 2028-08-24 | 2028-08-30 | 2028-08-31 | 2028-09-04 | 2028-09-08 | 2028-09-14
E34 | 2028-09-06 | 2028-09-07 | 2028-09-14 | 2028-09-19 | 2028-09-21 | 2028-09-21 | 2028-09-27 | 2028-09-28 | 2028-10-02 | 2028-10-06 | 2028-10-12
E35 | 2028-10-01 | 2028-10-02 | 2028-10-09 | 2028-10-14 | 2028-10-16 | 2028-10-16 | 2028-10-22 | 2028-10-23 | 2028-10-27 | 2028-10-31 | 2028-11-09
E36 | 2028-11-08 | 2028-11-09 | 2028-11-16 | 2028-11-21 | 2028-11-23 | 2028-11-23 | 2028-11-29 | 2028-11-30 | 2028-12-04 | 2028-12-08 | 2028-12-14
(¬) The timeframe for assessment of responses depends on the complexity and amount of data provided by the Marketing Authorisation Holder.
(*) The Agency strongly recommends submitting the application before the published submission deadline. This is to avoid missing the target start date as a result
of a technically invalid eCTD submission, in which case the submission is considered void and it needs to be re-despatched.
(~) Step applicable only if the submission falls (at least partially) under the remit of the PRAC (typically, when a RMP is submitted). For PRAC-led variations (including only
an RMP or final results of non-interventional PASS with no consequences to Product Information), only the PRAC Rapporteur produces an AR.
(**) Comments from CHMP and PRAC members are not made available to Applicants.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CHMP) members which create the need for the update.
(#) Step applicable only in case of CAT Opinion (not applicable in case a Request for Supplementary Information is adopted by the CAT).

## 30D Resp phase no clock stop
30-day immediate responses to RSI assessment timetable¬
| Deadline for Submission (*) | Re-start date | CAT Rapporteur AR | PRAC Rapporteur AR (~) | Comments from PRAC (**) (~) | Comments from CAT and CHMP (**) | Updated PRAC Rapporteur AR (***) (~) | Updated CAT Rapporteur AR (***) | CAT Request for Supplementary Information (RSI) or Opinion | CHMP Opinion (#)
F1 | 2025-12-23 | 2025-12-25 | 2026-01-13 | 2026-01-13 | 2026-01-16 | 2026-01-16 | 2026-01-19 | 2026-01-19 | 2026-01-23 | 2026-01-29
F2 | 2026-01-29 | 2026-01-30 | 2026-02-10 | 2026-02-10 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-26
F3 | 2026-02-26 | 2026-02-27 | 2026-03-10 | 2026-03-10 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-26
F4 | 2026-03-26 | 2026-03-27 | 2026-04-07 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-17 | 2026-04-23
F5 | 2026-04-21 | 2026-04-22 | 2026-05-05 | 2026-05-05 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-21
F6 | 2026-05-20 | 2026-05-21 | 2026-06-09 | 2026-06-09 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 2026-06-19 | 2026-06-25
F7 | 2026-06-25 | 2026-06-26 | 2026-07-07 | 2026-07-07 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 2026-07-17 | 2026-07-23
F8
F9 | 2026-08-12 | 2026-08-13 | 2026-09-01 | 2026-09-01 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 2026-09-11 | 2026-09-17
F10 | 2026-09-17 | 2026-09-18 | 2026-09-29 | 2026-09-29 | 2026-10-02 | 2026-10-02 | 2026-10-05 | 2026-10-05 | 2026-10-09 | 2026-10-15
F11 | 2026-10-15 | 2026-10-16 | 2026-10-27 | 2026-10-27 | 2026-10-30 | 2026-10-30 | 2026-11-03 | 2026-11-03 | 2026-11-06 | 2026-11-12
F12 | 2026-11-12 | 2026-11-13 | 2026-11-24 | 2026-11-24 | 2026-11-27 | 2026-11-27 | 2026-11-30 | 2026-11-30 | 2026-12-04 | 2026-12-10
F13 | 2026-12-23 | 2026-12-24 | 2027-01-12 | 2027-01-12 | 2027-01-15 | 2027-01-15 | 2027-01-18 | 2027-01-18 | 2027-01-22 | 2027-01-28
F14 | 2027-01-28 | 2027-01-29 | 2027-02-09 | 2027-02-09 | 2027-02-12 | 2027-02-12 | 2027-02-15 | 2027-02-15 | 2027-02-19 | 2027-02-25
F15 | 2027-02-26 | 2027-02-27 | 2027-03-16 | 2027-03-16 | 2027-03-19 | 2027-03-19 | 2027-03-22 | 2027-03-22 | 2027-03-24 | 2027-04-02
F16 | 2027-04-01 | 2027-04-02 | 2027-04-13 | 2027-04-13 | 2027-04-16 | 2027-04-16 | 2027-04-19 | 2027-04-19 | 2027-04-23 | 2027-04-30
F17 | 2027-04-29 | 2027-04-30 | 2027-05-11 | 2027-05-11 | 2027-05-14 | 2027-05-14 | 2027-05-18 | 2027-05-18 | 2027-05-21 | 2027-05-27
F18 | 2027-05-27 | 2027-05-28 | 2027-06-08 | 2027-06-08 | 2027-06-11 | 2027-06-11 | 2027-06-14 | 2027-06-14 | 2027-06-18 | 2027-06-24
F19 | 2027-06-24 | 2027-06-25 | 2027-07-06 | 2027-07-06 | 2027-07-09 | 2027-07-09 | 2027-07-12 | 2027-07-12 | 2027-07-16 | 2027-07-22
F20
F21 | 2027-08-11 | 2027-08-12 | 2027-08-31 | 2027-08-31 | 2027-09-03 | 2027-09-03 | 2027-09-06 | 2027-09-06 | 2027-09-10 | 2027-09-16
F22 | 2027-09-16 | 2027-09-17 | 2027-09-28 | 2027-09-28 | 2027-10-01 | 2027-10-01 | 2027-10-04 | 2027-10-04 | 2027-10-08 | 2027-10-14
F23 | 2027-10-14 | 2027-10-15 | 2027-10-26 | 2027-10-26 | 2027-10-29 | 2027-10-29 | 2027-10-29 | 2027-10-29 | 2027-11-05 | 2027-11-11
F24 | 2027-11-12 | 2027-11-13 | 2027-11-30 | 2027-11-30 | 2027-12-03 | 2027-12-03 | 2027-12-06 | 2027-12-06 | 2027-12-10 | 2027-12-16
F25 | 2027-12-22 | 2027-12-23 | 2028-01-11 | 2028-01-11 | 2028-01-14 | 2028-01-14 | 2028-01-17 | 2028-01-17 | 2028-01-21 | 2028-01-27
F26 | 27/01/2028 | 2028-01-28 | 2028-02-08 | 2028-02-08 | 2028-02-11 | 2028-02-11 | 2028-02-14 | 2028-02-14 | 2028-02-18 | 2028-02-24
F27 | 24/02/2028 | 2028-02-25 | 2028-03-07 | 2028-03-07 | 2028-03-10 | 2028-03-10 | 2028-03-13 | 2028-03-13 | 2028-03-17 | 2028-03-23
F28 | 21/03/2028 | 2028-03-22 | 04/04/2028 | 04/04/2028 | 07/04/2028 | 07/04/2028 | 10/04/2028 | 10/04/2028 | 2028-04-12 | 2028-04-21
F29 | 20/04/2028 | 2028-04-21 | 2028-05-02 | 2028-05-02 | 2028-05-05 | 2028-05-05 | 2028-05-08 | 2028-05-08 | 2028-05-12 | 2028-05-18
F30 | 20/05/2028 | 21/05/2028 | 2028-06-06 | 2028-06-06 | 2028-06-09 | 2028-06-09 | 2028-06-12 | 2028-06-12 | 2028-06-16 | 2028-06-22
F31 | 22/06/2028 | 2028-06-23 | 2028-07-04 | 2028-07-04 | 2028-07-07 | 2028-07-07 | 2028-07-10 | 2028-07-10 | 2028-07-14 | 2028-07-20
F32
F33 | 10/08/2028 | 11/08/2028 | 2028-08-29 | 2028-08-29 | 2028-09-01 | 2028-09-01 | 2028-09-04 | 2028-09-04 | 2028-09-08 | 2028-09-14
F34 | 14/09/2028 | 2028-09-15 | 2028-09-26 | 2028-09-26 | 2028-09-29 | 2028-09-29 | 2028-10-02 | 2028-10-02 | 2028-10-06 | 2028-10-12
F35 | 09/10/2028 | 2028-10-10 | 2028-10-21 | 2028-10-21 | 2028-10-24 | 2028-10-24 | 2028-10-27 | 2028-10-27 | 2028-10-31 | 2028-11-09
F36 | 09/11/2028 | 10/11/2028 | 2028-11-28 | 2028-11-28 | 2028-12-01 | 2028-12-01 | 2028-12-04 | 2028-12-04 | 2028-12-08 | 2028-12-14
(¬) This timetable is only applicable when minor issues remain and, if the variation involves the PRAC, a PRAC plenary discussion is not needed.
(*) The Agency strongly recommends submitting the application before the published submission deadline. This is to avoid missing the target start date as a result
of a technically invalid eCTD submission, in which case the submission is considered void and it needs to be re-despatched.
(~) Step applicable only if the submission falls (at least partially) under the remit of the PRAC (typically, when a RMP is submitted). For PRAC-led variations (including only
an RMP or final results of non-interventional PASS with no consequences to Product Information), only the PRAC Rapporteur produces an AR.
(**) Comments from CAT, CHMP and PRAC members are not made available to Applicants.
(***) An updated AR is optional and dependent on the comments received from committee (PRAC, CAT, CHMP) members which create the need for the update.
(#) Step applicable only in case of CAT Opinion (not applicable in case a Request for Supplementary Information is adopted by the CAT).

## Version tracking
Version 4
Dates for 2027 added in all tabs
Version 5
Dates for 2028 added in all tabs